## Sheet1
PROJECT NAME | Real-Time IoT Data Streaming Pipeline
PROJECT DELIVERABLE | Full-stack OSS data streaming system on AWS
SCOPE STATEMENT | Simulate, ingest, process, store, and visualize IoT data on AWS using open-source tools
START DATE | 06/10/2025 | END DATE | 08/18/2025 | OVERALL PROGRESS | 0%
TASK NAME | ASSIGNED TO | START DATE | END DATE | STATUS
Initialize GitHub repo and Overleaf report | Both | Week 1 | Week 2 | Not Started
Define architecture and finalize tech stack | Both | Week 1 | Week 2 | Not Started
Initialize Python CDK app and set up VPC | Sai Kiran | Week 2 | Week 2 | Not Started
Design EC2 layout and security groups | Varun | Week 2 | Week 2 | Not Started
Provision EC2 for Kafka (via CDK) | Sai Kiran | Week 3 | Week 4 | Not Started
Provision EC2 for Spark (via CDK) | Varun | Week 3 | Week 4 | Not Started
Research and implement Kafka install script | Sai Kiran | Week 4 | Week 4 | Not Started
Write Python Lambda sensor simulator | Varun | Week 4 | Week 4 | Not Started
Deploy Spark Structured Streaming job | Sai Kiran | Week 5 | Week 6 | Not Started
Integrate Spark with Kafka topic | Varun | Week 5 | Week 6 | Not Started
Write Spark output to PostgreSQL | Sai Kiran | Week 6 | Week 6 | Not Started
Write raw data to S3 (Parquet format) | Varun | Week 6 | Week 6 | Not Started
Set up Prometheus + Node Exporter on EC2 | Sai Kiran | Week 7 | Week 7 | Not Started
Deploy Alertmanager with alert rules | Varun | Week 7 | Week 7 | Not Started
Install Grafana and connect to RDS and Prometheus | Sai Kiran | Week 8 | Week 8 | Not Started
Build Grafana dashboards | Varun | Week 8 | Week 8 | Not Started
Integration testing of full pipeline | Both | Week 9 | Week 9 | Not Started
Add backup and failure recovery logic | Sai Kiran | Week 9 | Week 9 | Not Started
Finalize documentation and Overleaf report | Both | Week 10 | Week 10 | Not Started
Prepare final presentation slides | Both | Week 10 | Week 10 | Not Started